## Slide 1: Traditional Stage-Gate Overview
Gate 1
Stage 1
Gate 2
Stage 2
Gate 3
Stage 3
Gate 4
Stage 4
Gate 5
Stage 5
Gate Follow Through- Performance vs Launch Plan
Launch
Initial Idea Screen
Feasibility Check
Project Approval
Launch Decision
Market Trial Approval
Primary Investigation
Field Trial
Business Case
Development
Decision Point
Action Point
Stage 0 Idea Generation
Figure 1

## Slide 2: Gate 1 & Stage 1
Gate 1- Initial Idea Screen
Does the idea directly link to a customer(s) or if internal, end-users?
Does the idea create new potential business with existing customers?
Does the idea create new potential business with new customers?
Does the idea match our business strategies?
Does the idea warrant the commitment of resources?
Is all of the information provided?
Stage 1- Primary Investigation
Define the idea in 1-3 sentences
Define the scope in 1-3 sentences
Define the feasibility in 1-3 sentences
State any easily known market size, technical need and financial need
Gate 1
Stage 1
Idea screening
Primary Investigation
Figure 2

## Slide 3: Gate 2 & Stage 2
Gate 2- Feasibility Check
Which existing customer is the idea directly linked to?
Which new customers can we go to with this idea?
Does the idea, scope and feasibility still align with the business strategies?
Does the idea need to alter business strategies?
What are the preliminary resources needed?
Stage 2- Business Case
Team formation
Take the idea, scope and feasibility and add details
Perform marketing, sales, technical and operations analysis
Develop actions plans and time tables
Gate 2
Stage 2
Secondary screening
Business case
Figure 3

## Slide 4: Gate3 & Stage 3
Gate 3- Business Case Approval (The Money Gate)
Are the marketing, sales, technical, and operations analyses completed?
Are the resources available and committed to the project, including team members?
Have team members ensure they would have the project as part of their performance review?
Are timetables reasonable with measureable major action plans?
Stage 3- Development
Project team kick off meeting, identifying secondary team members
Develop more detailed action plans
Develop customer iterative action plan with what parameters and methods are being evaluated
(should turn into field trial plan)
Develop marketing campaign plan
Develop logistics and manufacturing plan
SKU creation by container with DP# and eventual naming convention
Gate 3
Stage 3
Project Approval
Development
Figure 4

## Slide 5: Gate 4 & Stage 4
Gate 4- Decision to go to Field Trail
Have we meet customer evaluation requirements and gotten their agreement?
Is the project plan updated?
Is the marketing campaign design done?
Is the 118 second message completed?
Are the SKU created?
Has product passed QC and repeatable?
Is IP and regulatory completed?
Stage 4- Field Trial
Value chain on process for trail
Compare lab evaluation data to field trial data
Write up case study
Get initial orders from trial customers
Identify target customers and being discussions
Gate 4
Stage 4
Decision to Field trial
Field Trail
Figure 5

## Slide 6: Gate 5 & Stage 5
Gate 5- Decision to Launch
Are initial target customers scheduled for the introduction?
Are sales goals established and in line with the budget?
Are support functions in place for technology, operations, and regulatory?
Are all SDS, TDS, case studies, presentations, and white papers available on web/intranet?
Are stocks built for immediate demand?
Stage 5- Launch
Product rollout
Measure against sales targets
Gate 5
Stage 5
Decision to Launch
Launch
Figure 6

## Slide 7: Performance Review To Launch Plan
Gate Follow Through
Have sales targets been achieved?
Has the product performed as expected from our point of view?
Has the product performed as expected from customers point of view?
What benefits were not realized initially that are now apparent?
Are the new benefits able to open the market to a great customer base?
What shortcomings does the product have?
Are the shortcomings able to be turned into a next-generation product that is a value add?
What other lessons were learned from this product launch to help improve the process?
What other targets, besides sales, were met? (i.e., better raw material costs, additional time efficiencies, additional equipment utilization for other projects, etc)
Figure 7